## Syslog
Task | Description | % Complete | Budgeted Hours | Budgeted Cost | Actual Hours | Actual Cost | Estimate to Complete | Total Estimate
0 | LogLogic
1 | Project Management - Planning, Execution, Monitoring, and Closure
2 | Project Management (Planning)
3 | Preliminary Setup
4 | Assign Resources |  | 2 | 420 | 2 | 420 | 0 | 420
5 | Preparation and Distribution of Checklists |  | 2 | 420 | 2 | 420 | 0 | 420
6 | System setup; Test, Dev and Production |  | 4 | 840 | 4 | 840 | 0 | 840
7 | Create initial templates; Issues, Risks, Estimate to Complete, and Status |  | 2 | 420 | 2 | 420 | 0 | 420
8 | Project Charter
9 | Create Project Charter |  | 6 | 1260 | 6 | 1260 | 0 | 1260
10 | Review Project Charter |  | 0 | 0 | 0 | 0 | 0 | 0
11 | Revise Project Charter |  | 2 | 420 | 2 | 420 | 0 | 420
12 | Project Charter Signoff |  | 0 | 0 | 0 | 0 | 0 | 0
13 | Project Schedule
14 | Create Project Schedule |  | 8 | 1680 | 8 | 1680 | 0 | 1680
15 | Review Project Schedule |  | 0 | 0 | 0 | 0 | 0 | 0
16 | Revise Project Schedule |  | 4 | 840 | 4 | 840 | 0 | 840
17 | Project Schedule Signoff |  | 0 | 0 | 0 | 0 | 0 | 0
18 | Final Setup
19 | Create Actual Estimate to Complete Report |  | 2 | 420 | 2 | 420 | 0 | 420
20 | Create Actual Status Report |  | 2 | 420 | 2 | 420 | 0 | 420
21 | Risk Identification and Mitigation |  | 2 | 420 | 2 | 420 | 0 | 420
22 | Prepare Kickoff Presentation |  | 2 | 420 | 2 | 420 | 0 | 420
23 | Conduct Kick-Off Meeting |  | 2 | 420 | 2 | 420 | 0 | 420
24 | Project Management (Execution and Monitoring)
25 | Project Management (Status, Issue Resolution, Risk Mgt, Quality Mgt, Change Mgt) |  | 100 | 21000 | 64.5 | 13545 | #DIV/0! | #DIV/0!
26 | Project Management (Closure)
27 | Project Closure Preparation of Documents |  | 2 | 420 | 1.5 | 315 | 0 | 315
28 | Project Closure Meeting |  | 2 | 420 | 1 | 210 | 0 | 210
29 | Final Procedures to Close Project |  | 2 | 420 | 2 | 420 | 0 | 420
31 | Hardware and Software Prerequisites
32 | Hardware Prerequisites
33 | Create Procurement Plan |  | 0 | 0 | 0 | 0 | 0 | 0
34 | Approval of Procurement Plan |  | 0 | 0 | 0 | 0 | 0 | 0
35 | Hardware Installation |  | 0 | 0 | 0 | 0 | 0 | 0
36 | Software Prerequisites
37 | Install SQL |  | 0 | 0 | 0 | 0 | 0 | 0
39 | Education
40 | Attend Security Command Center Class |  | 0 | 0 | 0 | 0 | 0 | 0
42 | Communication and Production Rollout Plans
43 | Communication Plan
44 | Create Communication Plan |  | 0 | 0 | 0 | 0 | 0 | 0
45 | Communication Plan Meeting |  | 0 | 0 | 0 | 0 | 0 | 0
46 | Approval of Communication Plan |  | 0 | 0 | 0 | 0 | 0 | 0
47 | Production Rollout Plan
48 | Create Production Rollout Plan |  | 0 | 0 | 0 | 0 | 0 | 0
49 | Production Rollout Plan Meeting |  | 0 | 0 | 0 | 0 | 0 | 0
50 | Approval of Production Rollout Plan |  | 0 | 0 | 0 | 0 | 0 | 0
51 | Submit Request For Change (RFC's) to Change Board |  | 0 | 0 | 0 | 0 | 0 | 0
53 | Business Requirements and Architectural Design
54 | Business Requirements
55 | BR: Kick-Off Meeting |  | 2 | 380 | 2 | 380 | 0 | 380
56 | BR: Review Questionnaires and Provided Documentation |  | 8 | 1520 | 2 | 380 | 0 | 380
57 | BR: Conduct Demonstration with System Administrators |  | 6 | 1140 | 2 | 380 | 0 | 380
58 | BR: Conduct Workshops with Business Owners |  | 28 | 5320 | 25 | 4750 | 0 | 4750
59 | BR-Consultant: Conduct Workshops with Business Owners |  | 0 | 0 | 0 | 0 | 0 | 0
60 | Document Business Requirements |  | 28 | 5320 | 19.5 | 3705 | #DIV/0! | #DIV/0!
61 | Review Business Requirements |  | 0 | 0 | 0 | 0 | 0 | 0
62 | Revise Business Requirements |  | 8 | 1520 | 0 | 0 | 0 | 0
63 | Business Requirements Signoff |  | 0 | 0 | 0 | 0 | 0 | 0
64 | Architectural Design
65 | AD: Kick-Off Meeting |  | 2 | 420 | 2 | 420 | 0 | 420
66 | AD: Review Questionnaires and Provided Documentation |  | 8 | 1680 | 2 | 420 | 0 | 420
67 | AD: Conduct Demonstration with System Administrators |  | 6 | 1260 | 2 | 420 | 0 | 420
68 | AD: Conduct Workshops with Business Owners |  | 28 | 5880 | 25 | 5250 | 0 | 5250
69 | Document Architectural Design |  | 28 | 5880 | 28 | 5880 | 0 | 5880
70 | Review Architectural Design |  | 0 | 0 | 0 | 0 | 0 | 0
71 | Revise Architectural Design |  | 8 | 1680 | 21 | 4410 | 0 | 4410
72 | Architectural Design Signoff |  | 0 | 0 | 0 | 0 | 0 | 0
74 | Development - Install and Configure LogLogic
75 | Install Development Environment
76 | Dev: Install Windows 200x & Service Packs |  | 4 | 760 | 0 | 0 | 0 | 0
77 | Dev: Install MS-SQL and service packs |  | 4 | 760 | 0 | 0 | 0 | 0
78 | Dev: Create database/user for Portal and Audit |  | 4 | 760 | 1 | 190 | 0 | 190
79 | Dev: Install Audit data tools, policy manager and client |  | 4 | 760 | 2 | 380 | 0 | 380
80 | Dev: Install Auditor, Auditor, and Aries |  | 4 | 760 | 3 | 570 | #DIV/0! | #DIV/0!
81 | Dev: Install LogLogic Server |  | 4 | 760 | 3 | 570 | 0 | 570
82 | Dev: Install Audit and LogLogic client |  | 4 | 760 | 4 | 760 | 0 | 760
83 | Dev: Install LogLogic product integration kits |  | 4 | 760 | 2 | 380 | #DIV/0! | #DIV/0!
84 | Admin working along side consultant during automation |  | 0 | 0 | 0 | 0 | 0 | 0
85 | Configuration
86 | Test baseline operation of Audit |  | 8 | 1520 | 8 | 1520 | #DIV/0! | #DIV/0!
87 | Configure 10 Audit Policies |  | 24 | 4560 | 27 | 5130 | #DIV/0! | #DIV/0!
88 | Configure Addiitonal Audit Policies |  | 0 | 0 | 0 | 0 | 0 | 0
89 | Configure 4 custom LogLogic menu profiles |  | 32 | 6080 | 9 | 1710 | #DIV/0! | #DIV/0!
90 | Configure additional custom LogLogic menu profiles |  | 0 | 0 | 0 | 0 | 0 | 0
91 | Configure 4 custom LogLogic views for roles (ex. CIO, CSO, Global Enterprise Security, Operations Staff) |  | 32 | 6080 | 13 | 2470 | #DIV/0! | #DIV/0!
92 | Configure additional custom LogLogic views for roles |  | 0 | 0 | 0 | 0 | 0 | 0
93 | Configure 5 Integration Kits and Audit log components |  | 40 | 7600 | 3 | 570 | #DIV/0! | #DIV/0!
94 | Configure Additional Integration Kits and Audit log components |  | 0 | 0 | 0 | 0 | 0
95 | Configure 5 HTML reports |  | 40 | 7600 | 4 | 760 | #DIV/0! | #DIV/0!
96 | Configure Additional HTML reports |  | 0 | 0 | 0 | 0 | 0 | 0
97 | Admin working along side consultant during configuration |  | 0 | 0 | 0 | 0 | 0 | 0
98 | Interfaces
99 | Interface x
100 | Install Client |  | 0 | 0 | 0 | 0 | 0 | 0
101 | Configure Interface |  | 0 | 0 | 0 | 0 | 0 | 0
102 | Create Report |  | 0 | 0 | 0 | 0 | 0 | 0
103 | Package Solutions
104 | Create Automated Windows Installation Package |  | 24 | 4560 | 11 | 2090 | #DIV/0! | #DIV/0!
105 | Create Automated UNIX Installation Package |  | 16 | 3040 | 0 | 0 | 0 | 0
106 | Admin working along side consultant during automation |  | 0 | 0 | 0 | 0 | 0 | 0
107 | Walkthrough
108 | Verification that Development is complete and the Product is ready for System Test |  | 4 | 760 | 0 | 0 | 0 | 0
109 | Modifications from Walkthrough |  | 4 | 760 | 0 | 0 | 0 | 0
110 | Development Complete |  | 0 | 0 | 0 | 0 | 0 | 0
112 | System Testing
113 | Install Test Environment
114 | Install LogLogic on Windows Servers |  | 4 | 760 | 11 | 2090 | #DIV/0! | #DIV/0!
115 | Install LogLogic on UNIX Servers |  | 4 | 760 | 6 | 1140 | #DIV/0! | #DIV/0!
116 | Install LogLogic on other Test Servers |  | 0 | 0 | 0 | 0 | 0 | 0
117 | Test Cases and Test Plan
118 | Create Test Cases and Test Plan |  | 24 | 4560 | 0 | 0 | 0 | 0
119 | Create Additional Test Cases and Test Plan |  | 0 | 0 | 0 | 0 | 0 | 0
120 | Review Test Cases and Test Plan |  | 0 | 0 | 0 | 0 | 0 | 0
121 | Revise Test Cases and Test Plan |  | 8 | 1520 | 0 | 0 | 0 | 0
122 | Test Execution
123 | Execute System Test |  | 20 | 3800 | 2 | 380 | 0 | 380
124 | Consultant: Execute System Test |  | 0 | 0 | 0 | 0 | 0 | 0
125 | Support System Test |  | 16 | 3040 | 8 | 1520 | 0 | 1520
126 | Review Final Test Results |  | 4 | 760 | 0 | 0 | 0 | 0
127 | Testing Complete |  | 0 | 0 | 0 | 0 | 0 | 0
129 | Client Training
130 | Knowledge Transfer to the Clients Trainer |  | 16 | 3040 | 0 | 0 | 0 | 0
131 | Identification of groups/individuals to be trained |  | 0 | 0 | 0 | 0 | 0 | 0
132 | Schedule Training |  | 0 | 0 | 0 | 0 | 0 | 0
133 | Define Training Logistics |  | 0 | 0 | 0 | 0 | 0 | 0
134 | Develop Training Documentation |  | 0 | 0 | 0 | 0 | 0 | 0
135 | Train End users |  | 0 | 0 | 0 | 0 | 0 | 0
136 | Training Complete |  | 0 | 0 | 0 | 0 | 0 | 0
138 | Production
139 | Production Rollout
140 | Prod: Install LogLogic on 10 Servers |  | 16 | 3040 | 16 | 3040 | 0 | 3040
141 | Prod-Consultant: Install LogLogic on 90 Servers |  | 0 | 0 | 0 | 0 | 0 | 0
142 | Prod: Install LogLogic on additional Production Servers |  | 0 | 0 | 0 | 0 | 0 | 0
143 | Documentation
144 | Document Changes to Base System |  | 16 | 3040 | 12 | 2280 | 0 | 2280
145 | Document Routine Maintenance Procedures |  | 16 | 3040 | 7 | 1330 | 0 | 1330
146 | Production Complete |  | 0 | 0 | 0 | 0 | 0 | 0
148 | Ongoing Activities
149 | Attend Meetings, (2 - 1 hour meetings a week, 1 Status and 1 Technical) (2 hours a week) |  | 28 | 5320 | 4 | 760 | #DIV/0! | #DIV/0!
150 | Knowledge Transfer on LogLogic up to 2 hours a week |  | 30 | 5700 | 24 | 4560 | 0 | 4560
152 | Reserves
153 | Time not in Plan in case some problems arise |  | 40 | 7600 | 0 | 0 | 0 | 0
154 | R8.0 Install and Reconfigure
155 | Backup Existing Directories and Uninstall Software |  | 4 | 760 | 4 | 760 | 0 | 760
156 | Prod:Create database/user for Portal and Audit |  | 1 | 190 | 1 | 190 | 0 | 190
157 | Prod: Install Audit data tools, policy manager and client |  | 4 | 760 | 4 | 760 | 0 | 760
158 | Prod: Install Auditor, Auditor |  | 2 | 380 | 4 | 760 | 0 | 760
159 | Prod: Install LogLogic Server |  | 4 | 760 | 4 | 760 | 0 | 760
160 | Prod: Install LogLogic product integration kits |  | 1 | 190 | 1 | 190 | 0 | 190
161 | Prod: Install Audit Client, LogLogic agent on CheckPoint Server |  | 3 | 570 | 2 | 380 | 0 | 380
162 | Prod: Install Audit Client, LogLogic agent on CiscoWorks Server |  | 3 | 570 | 0.5 | 95 | 0 | 95
163 | Prod: Install Audit Client, LogLogic agent on Cisco Secure ACS Server |  | 3 | 570 | 0.5 | 95 | 0 | 95
164 | Prod: Install LogLogic agent on DB Server |  | 2 | 380 | 2 | 380 | 0 | 380
165 | Verify, modify Audit Policies |  | 3 | 570 | 3 | 570 | 0 | 570
166 | Configure Menu Profiles and Views |  | 8 | 1520 | 7 | 1330 | 0 | 1330
167 | Configure HTML reports |  | 2 | 380 | 1 | 190 | 0 | 190
Totals |  |  | 844 | 164880 | 453.5 | 89945 | #DIV/0! | #DIV/0!
Planned hours, previous week 453 + this week 46
Summary:
| Cost Status = CPI, Budgeted cost / Total Estimate = |  | - | Cost - we are under budget.
| Schedule Status = SPI, Planned Hours / Actual hours = |  | - | Schedule - we are ahead of Schedule.