## Legend
Instructions to Users: Respond to the questions below by entering values in the turquoise filled cells (Column F: Value). Values for Boolean DataType should be 0 for False and 1 for True. Bright Green filled cells in Estimate (in Days) Column on the next spreadsheet tab show calculations of effort (NOT duration) in days per task with applicable rollups in the Work Breakdown Structure. These values can be copied into a MS Project Schedule as Work (NOT duration). Bright Green filled cells in Row 2, after the Effort column, on the next spreadsheet show totals of effort (NOT duration) in days by Role. Note: This spreadsheet has been protected (without a password) to prevent accidental modification.

## Variables
Estimating Variable | Question - English | Description | DataType | Formula | Value
CLNumWorkflowTasks | How Many tasks, on an average, does each Workflow contain? | Average number of steps in the service desk change order workflow. | Integer |  | 5
CLNumWorkflows | How Many Workflows will be created? | Corresponds to the number of change workflows setup as part of the integration. E.g one workflow for managing change, one for creating projects, etc. | Integer |  | 2
CLNumProj | How Many Projects are Included? | The average number of applications that are supported via service desk. There will be one project in clarity created for each application. | Integer |  | 5
CLNumUsers | How Many Unique Users need to be set up? | Total number of users between Service Desk and Clarity. These will need to be synchronized. | Integer |  | 20

## SDIC
Name | Formula | Estimate (in Days) | Roles | Predecessors | Project Manager | Consultant | Architect
Service Desk Integration with Clarity |  | 18.225 |  |  | 3.2875 | 12.8125 | 2.125
Integration Set Up |  | 18.225
Technical Startup |  | 3.9125
Perform Engagement Management Setup Activities | 2.25+(.15*(CLNumUsers/20)+(.1*CLNumWorkflows)+(.125*CLNumProj)+.00625*CLNumWorkflows*CLNumWorkflowTasks) | 3.2875 | Project Manager
Prepare for Engagement | 0.125 | 0.125 | Consultant
Review Implementation Information with Client | 0.25 | 0.25 | Consultant | 6
Review Project Schedule with Client | 0.25 | 0.25 | Consultant | 7
Architecture and Design |  | 4.625
Conduct Briefing with Client Project Sponsor | 0.25 | 0.25 | Consultant | 8,4
Conduct Kick-Off Session | 0.125 | 0.125 | Consultant | 10
Gather Service Desk Information | 0.25 | 0.25 | Architect,Consultant | 11
Gather Clarity Information | 0.25 | 0.25 | Architect,Consultant | 12
Gather Users and Role Information | iF(0.25*(CLNumUsers/50)<0.25,.25,.25*CLNumUsers/50) | 0.25 | Architect,Consultant | 13
Gather Service Desk to Clarity Integration Information | if(0.25*CLNumWorkflows<1,1,(0.25*CLNumWorkflows)) | 1 | Architect,Consultant | 14
Create Solution Architecture Specification | 2 | 2 | Architect,Consultant | 15
Review Solution Architecture Specification with Client | 0.5 | 0.5 | Architect,Consultant | 16
Service Desk Configuration |  | 2.6875
Install Integration Files | 0.125 | 0.125 | Consultant | 17
Configure the Integration Workflow in Service Desk | 0.03125*CLNumWorkflows*CLNumWorkflowTasks | 0.3125 | Consultant | 19
Configure the Service Desk Forms | 0.5*CLNumWorkflows | 1 | Consultant | 20
Create Integration Tables and Populate with Data | 0.5 | 0.5 | Consultant | 21
Provision User IDs | iF(0.25*(CLNumUsers/50)<0.25,.25,.25*CLNumUsers/50) | 0.25 | Consultant | 22
Configure Parameter File for Clarity Integration | 0.25 | 0.25 | Consultant | 23
Test Service Desk Configuration | 0.25 | 0.25 | Consultant | 24
Clarity Configuration |  | 3.375
Configure Custom Fields for Project Tasks | 0.5 | 0.5 | Consultant | 25
Provision User IDs | iF(0.25*(CLNumUsers/50)<0.25,.25,.25*CLNumUsers/50) | 0.25 | Consultant | 27
Create Maintenance Projects for Applications | .125*CLNumProj | 0.625 | Consultant | 28
Configure Views | 0.5 | 0.5 | Consultant | 29
Install Integration Files | 0.5 | 0.5 | Consultant | 30
Configure Parameter Files | 0.25 | 0.25 | Consultant | 31
Test Clarity Configuration | 0.5 | 0.5 | Consultant | 32
Initialize Interface | 0.25 | 0.25 | Consultant | 33
Configuration Review |  | 2.5
Execute System Test Plan | 1 | 1 | Consultant | 34
Conduct Knowledge Transfer Session for Admin | 0.5 | 0.5 | Consultant | 36
Conduct Knowledge Transfer Session for End Users | 0.5 | 0.5 | Consultant | 37,36
Complete Documentation | 0.5 | 0.5 | Consultant | 38,36
Technical Closure |  | 1.125
Prepare for Final Review | 0.125 | 0.125 | Consultant | 39
Review Installation with Client Project Sponsor | 0.5 | 0.5 | Consultant | 41
Conduct Final Review Session | 0.5 | 0.5 | Consultant | 42